Pharmatiya Health

Phase 1 — Website Rebuild

What we will build, and what we need from you

Prepared by Vaelo Creative

hello@vaelocreative.com

August 2026

# What we are doing

Rebuilding pharmatiya.net from scratch as a six-page static website. The current Squarespace site has placeholder images, an empty shopping cart, generic copy, and no evidence of Pharmatiya’s real expertise. The new site fixes all of that.

The six pages:

## Home

- Clear positioning statement for HEOR and RWE buyers

- Three service lines with real descriptions, not generic cards

- Proof section: 25+ years, 1,000+ synopses, named therapeutic areas

- NextGen AI teaser linking to the dedicated product page

- One primary CTA: book a consultation

## Services

- Each service framed as a problem the buyer recognises, then Pharmatiya’s approach

- Real deliverables listed per service, not vague promises

- HEOR data-graphics (forest plots, Kaplan-Meier curves) as visual proof

- Pricing guidance or engagement model if Pharmatiya supplies it

## Evidence (new page)

- Anonymised case studies showing methods and outcomes

- Dataset coverage map (payer, provider, claims data)

- Therapeutic area expertise grid

- Downloadable samples or gated content if Pharmatiya wants lead capture

## NextGen AI (new page)

- Product landing page for the AI synopsis tool

- Three-step workflow explained visually (Feasibility → Retrospective → Pragmatic Outreach)

- Trust features: no PHI uploads, mandatory human expert review

- Transparent about the underlying model (disclosure, not disclaimer)

- Access request or demo CTA

## About

- 25-year track record made scannable, not buried in paragraphs

- Team section with real photos and credentials

- Dataset and partner coverage

- Company timeline or milestones if supplied

## Contact

- Segmented routing: new clients, existing clients, press/partners

- Direct consultation booking (calendar integration if provided)

- Office location: New York, NY 10280

- Quarterly Insights Digest signup (currently mentioned but not subscribable)

# What gets fixed

These are the specific problems on the current site that the rebuild resolves:

- Placeholder images — Two pages still show images literally named ‘Placeholder’ in the source code. Replaced with real visuals.

- Empty shopping cart — A leftover from the Squarespace template. Removed entirely.

- Generic copy — Sentences like ‘tailored solutions’ and ‘actionable insights’ repeated across all pages. Rewritten with specifics.

- No proof — Zero case studies, no named engagements, no outcome figures, no team photos. Evidence page and proof sections fix this.

- AI tool invisible — The biggest differentiator barely appears on the current site. Gets its own dedicated page.

- Dense About page — The one page with real substance buries it in long paragraphs. Made scannable.

- One contact form — The entire lead-generation system. Replaced with segmented routing and booking.

- Digest not subscribable — Mentioned on the site but captures nothing. Real signup added.

# How it will look

The brief is explicit: it must not look AI-generated. That means:

We will not use:

- Stock photography of people in labs

- Three identical feature cards in a row

- Gradient hero backgrounds

- Generic icon sets as decoration

- Centred-everything layouts

We will use:

- Real HEOR data-graphics as design elements (Kaplan-Meier curves, forest plots, cost-effectiveness planes)

- Specificity over adjectives: real numbers, named datasets, concrete deliverables

- Asymmetric, varied layouts that break the template pattern

- A restrained, professional register closer to IQVIA than a SaaS startup

- Semantic HTML, full keyboard navigation, WCAG AA accessibility

- Responsive design from 320px mobile to desktop

# Timeline

Seven weeks from kickoff to launch-ready.

| Week | Phase | What happens |
| --- | --- | --- |
| 1 | Discovery | Content audit, gather all inputs from Pharmatiya, finalise sitemap |
| 2 | Design | Design system, homepage layout, mobile and desktop compositions |
| 3 | Design review | Pharmatiya reviews and approves design direction (GATE) |
| 4–5 | Build | All six pages built, responsive, accessible, real content placed |
| 6 | Content + QA | Final content from Pharmatiya, cross-browser testing, accessibility audit |
| 7 | Launch | DNS, redirects, analytics, go-live (GATE) |

Two gates require Pharmatiya sign-off before we proceed. If sign-off is delayed, the timeline shifts by the same number of days.

# Investment

|  | Amount |
| --- | --- |
| Phase 1 total | ₹2,85,000 |
| On signing (40%) | ₹1,14,000 |
| On design approval (30%) | ₹85,500 |
| On launch (30%) | ₹85,500 |

All amounts exclude GST. Pricing is placeholder pending Vaelo’s confirmed rate card.

Third-party costs (paid by Pharmatiya, not included above):

- Licensed typeface: ~$200–500 one-time

- Hosting and domain: depends on provider chosen

- Calendar booking tool (if used): ~$10–15/month

- Email platform for Digest signup: free tier likely sufficient

# What we need from Pharmatiya

We cannot build a credible site without real content. The items below are listed in order of when we need them.

| # | Item | Why | When |
| --- | --- | --- | --- |
| 1 | Team photographs (headshots, office, working) | About page needs real people. No stock photos. | Before Week 2 |
| 2 | Case study material (2–3 anonymised) | Evidence page is empty without this. Strongest proof of expertise. | Before Week 4 |
| 3 | Service descriptions reviewed | We draft; Pharmatiya verifies accuracy. Nothing published without sign-off. | Before Week 4 |
| 4 | Dataset name clearance | Aetna/CVS, Cigna, Intermountain — can we name them publicly? Yes or no. | Week 1 |
| 5 | NextGen AI product details | Screenshots, demo flow, features and limitations for the product page. | Before Week 4 |
| 6 | Contact routing preferences | Who gets enquiries? Separate routes? Calendar link for booking? | Week 1 |
| 7 | Typeface decision | System fonts are an AI-generated tell. We suggest options; ~$200–500 budget. | Before Week 2 |
| 8 | Logo in vector format | SVG or AI file for sharp rendering at all sizes. | Before Week 2 |
| 9 | Compliance review windows | Any outcome or regulatory claim needs internal review. We need turnaround time. | Week 1 |
| 10 | Hosting preference | Current site is Squarespace. New build is static and can go anywhere. | Before Week 5 |

Items marked ‘Week 1’ are needed at kickoff. Late inputs delay the timeline by the same amount.

# Not included in Phase 1

These are scoped for later phases or are separate engagements:

- Brand identity redesign (logo, colour palette, brand guidelines) — Phase 2

- NextGen AI tool development, onboarding, or audit trail — Phase 3

- Client portal or login system — Phase 3

- Blog or content management system

- E-commerce or payment processing

- Mobile app

- Ongoing content writing or SEO retainer

- Video production

- Paid advertising or media buying

- HIPAA compliance consulting

Vaelo Creative

hello@vaelocreative.com

Working document — pending rate card confirmation.