Phase 1 · Delivery roadmap · Architecture approved

Pharmatiya Health: Road to Launch

Seven weeks from kickoff to go-live, two sign-off gates, ten client inputs and one hard dependency chain — sequenced so nothing waits on anything it does not have to.

| Prepared by | Issued | Kickoff | Launch target |
| --- | --- | --- | --- |
| Vaelo Creative | 3 September 2026 | Mon 7 September 2026 | Fri 23 October 2026 |

| Weeks to launch | Sign-off gates | Client inputs | Due in week 1 | Pages to build |
| --- | --- | --- | --- | --- |
| 7 | 2 | 10 | 3 | 6 |

# 01  Where we are

Stages 1–10 are complete and approved. That work sat ahead of the contracted seven weeks, so Week 1 starts with the architecture already settled rather than still being argued.

| Delivered | Covers | Status |
| --- | --- | --- |
| Existing site audit | Sitemap, navigation, functionality, content, UX and visual problems — DOM-verified against the live site | Approved |
| Retain / improve / remove matrix | 22 elements decided; task-preservation check completed | Approved |
| Audience & information architecture | Four buying intents, six-page sitemap, page objectives and CTAs | Approved |
| User flows | Five journeys, desktop and mobile | Approved |
| Wireframes | All six pages, desktop and 375px, clickable prototype | Approved |
| Visual & design-system direction | Grid, type scale, colour tokens, components, accessibility baseline | Approved |

What this buys us Week 1 was scoped in the brief as content audit, input gathering and sitemap finalisation. Two of those three are already done. The week therefore compresses to chasing the four Week-1 inputs and standing up the repository — which means design can start earlier, and the schedule carries roughly three days of slack it would not otherwise have.

# 02  The critical path

Only one chain actually determines the launch date. Everything else has float.

| Week | Stage | Gated by |
| --- | --- | --- |
| 1 | Inputs 4 · 6 · 9 cleared | Pharmatiya — zero float |
| 2 | Design system + homepage compositions | Inputs 1 · 7 · 8 |
| 3 | GATE 1 — design approval | Written sign-off |
| 4–5 | Build: six pages, responsive, accessible | Inputs 2 · 3 · 5 |
| 6 | Content placement + QA + accessibility audit | Final copy, compliance sign-off |
| 7 | GATE 2 — launch: DNS, redirects, analytics | Written go-live approval, input 10 |

Float available

- Inputs 2 · 3 · 5 — roughly 3 weeks. Needed by Week 4, requested now.

- Input 10 (hosting) — roughly 4 weeks. Blocks deployment only, not build.

- Inputs 1 · 7 · 8 — roughly 1 week. They gate design, not architecture.

- Inputs 4 · 6 · 9 — none. These are the only items on the critical path.

The one rule that governs the date Both gates require Pharmatiya sign-off before we proceed. If sign-off is delayed, the timeline shifts by the same number of days — it does not compress. The same applies to Week-1 inputs: they are the only items with zero float, and a week’s delay on dataset clearance is a week’s delay on launch.

# 03  Week by week

Week 1  7–11 Sep   DISCOVERY

### Kickoff and input gathering

Architecture is settled, so this week is about unblocking design and build. The four Week-1 inputs are the entire point of it.

Vaelo does

- Kickoff call, walk the approved wireframes

- Stand up the Next.js repository and CI

- Draft copy for Home and Services

- Issue the input request with owners and dates

- Recommend a form handler and hosting option

Pharmatiya does

- Input 4 — dataset name clearance: yes or no per organisation

- Input 6 — contact routing and calendar link

- Input 9 — compliance review turnaround time

- Decide the public product name

- Confirm or withdraw the “1,000+ synopses” figure

Exit criteria Four Week-1 inputs received. Product name decided. Repository running with a deploy preview. Design can start Monday without open questions.

Week 2  14–18 Sep   DESIGN

### Design system and homepage composition

Turning the approved wireframes into a resolved visual system, with the homepage as the proof of it.

Vaelo does

- Finalise design tokens: colour, type scale, spacing, grid

- Licence and set the display typeface

- Homepage composition, desktop and mobile

- Draw the real HEOR figures: Kaplan–Meier, forest plot, cohort diagram, cost-effectiveness plane

- Component inventory against the wireframes

Pharmatiya does

- Input 1 — team, office and working photography

- Input 7 — typeface decision (~$200–500)

- Input 8 — logo in vector format (SVG or AI)

- Review draft Home and Services copy

Exit criteria Homepage composed at both breakpoints, tokens locked, figures drawn, remaining five pages specified against the system. Ready to present.

Week 3  21–25 Sep   GATE 1

### Design review and approval

The first contractual gate. Nothing is built until this closes.

Vaelo does

- Present design direction and homepage

- Walk the remaining five page designs

- Consolidate feedback into one revision round

- Reissue for sign-off

Pharmatiya does

- Review and consolidate internal feedback into a single response

- Approve the design direction in writing

- Release the 30% design-approval payment

Gate condition Written design approval. One consolidated revision round is included; a second round or a change of direction after approval moves the launch date and is quoted separately.

Weeks 4–5  28 Sep – 9 Oct   BUILD

### Front-end implementation

Next.js, React, TypeScript, Tailwind. Statically exported. Build order is set out in section 04.

Vaelo does

- Tokens, layout primitives, UI components

- Evidence components: forest plot, Kaplan–Meier, dataset map, therapeutic matrix

- All six pages, responsive at six breakpoints

- Contact form with routing, validation and states

- Accessibility built in, not retrofitted

- Deploy previews on every commit

Pharmatiya does

- Input 2 — 2–3 anonymised case studies

- Input 3 — service descriptions verified

- Input 5 — NextGen AI screenshots, features, limitations

- Input 10 — hosting preference

- Review preview builds as pages land

Exit criteria Six pages built and responsive, real content placed where supplied, placeholders clearly marked where not. Form submitting to a live endpoint. Preview URL shared.

Week 6  12–16 Oct   CONTENT + QA

### Final content, testing and audit

The week where anything still marked “to provide” either arrives or gets cut.

Vaelo does

- Place final copy and photography

- Accessibility audit: keyboard, screen reader, contrast, headings

- Cross-browser: Chrome, Safari, Firefox, Edge, iOS, Android

- Responsive check at 320, 375, 768, 1024, 1280, 1440+

- Core Web Vitals and image optimisation

- SEO: titles, meta, OG, schema, sitemap, robots

- Old-versus-new functionality audit

Pharmatiya does

- Final copy approval, page by page

- Compliance sign-off on any outcome or regulatory claim

- Confirm what ships and what is deferred

- Provide DNS access ahead of Week 7

Exit criteria Zero placeholder images. Zero unapproved claims. WCAG AA verified. Functionality audit signed off. Launch-ready build on a staging URL.

Week 7  19–23 Oct   GATE 2

### Launch

The second contractual gate. Go-live requires written approval.

Vaelo does

- Configure DNS and TLS

- Apply 301 redirects from the Squarespace URLs

- Install analytics and form notifications

- Submit sitemap; verify indexing

- Post-launch check at 24 and 72 hours

- Hand over repository, assets and documentation

Pharmatiya does

- Approve go-live in writing

- Confirm Squarespace cancellation timing

- Test the contact routes end to end and confirm receipt

- Release the final 30% payment

Gate condition Written go-live approval, DNS access, and confirmed receipt of a test enquiry through each of the three contact routes.

## Redirect map to be applied at launch

| Old URL | New URL | Type |
| --- | --- | --- |
| /home | / | 301 |
| /about | /about | Unchanged |
| /services | /services | Unchanged |
| /contact | /contact | Unchanged |
| /new-dropdown | /nextgen-ai | 301 |
| /cart | / | 301 — cart removed |

# 04  Build order, Weeks 4–5

Foundations first, then the components that carry credibility, then the pages that depend on them. Contact is built last because it is the only stateful page and needs the hosting decision.

| # | Stage | Detail |
| --- | --- | --- |
| 01 | Project foundation | Next.js with static export, TypeScript strict, Tailwind configured against the approved tokens. Base layout, fonts self-hosted and subset. |
| 02 | Layout components | Header, Navigation, MobileNavigation with focus trap, Footer. Skip link and landmarks. Keyboard-tested before anything else is built on top. |
| 03 | UI primitives | Button, Input, SectionHeader, DataLabel. All states defined once: default, hover, focus, disabled, error. |
| 04 | Evidence components | ForestPlot, KaplanMeierGraphic, DatasetMap, TherapeuticMatrix, CaseStudy. Hand-authored inline SVG, each with a text alternative describing the finding. |
| 05 | Home | Assembles Hero, Proof, Services, NextGenTeaser, CTA. Built first because it exercises the most components and surfaces system gaps early. |
| 06 | Services and Evidence | The two content-heaviest pages, sharing the service spine and the evidence components. Deep-link anchors verified against the homepage. |
| 07 | NextGen AI and About | Workflow diagram with the review bar; timeline and team grid. Both degrade gracefully if photography or product detail has not arrived. |
| 08 | Contact | ContactRouting with conditional fields, validation, live-region errors and a real success state. Last, because it depends on the hosting and form-handler decision. |
| 09 | Responsive and accessibility pass | Every page at six widths. Axe and manual screen-reader testing. Contrast verified against the final palette, not the draft one. |

Decision needed by Week 4 A statically exported site cannot process form submissions on its own. The contact form needs an endpoint — a form service, a serverless function, or the host’s built-in handler. This follows from input 10 and we will recommend an option in Week 1, but it must be settled before the Contact page is built.

# 05  Input schedule

Ten items, in the order they block work. Dates assume a 7 September kickoff.

| # | Input | Blocks | Due | Float |
| --- | --- | --- | --- | --- |
| 4 | Dataset name clearance | Evidence coverage, About, Home band | Fri 11 Sep | None |
| 6 | Contact routing & calendar | Contact page routing and booking | Fri 11 Sep | None |
| 9 | Compliance review windows | NextGen AI trust section, all claims | Fri 11 Sep | None |
| 1 | Team & office photography | About hero and team section | Fri 18 Sep | ~1 week |
| 7 | Typeface decision | Entire type system | Fri 18 Sep | ~1 week |
| 8 | Vector logo | Header, footer, favicon, brand colours | Fri 18 Sep | ~1 week |
| 2 | Case study material | Evidence case studies | Fri 2 Oct | ~3 weeks |
| 3 | Service descriptions verified | Services copy and naming | Fri 2 Oct | ~3 weeks |
| 5 | NextGen AI product detail | The whole NextGen AI page | Fri 2 Oct | ~3 weeks |
| 10 | Hosting preference | Form handling, deployment, redirects | Fri 9 Oct | ~4 weeks |

Two decisions we still need from you Product naming. NextGen AI or RWE - Builder as the public name? The page URL, the navigation label, the redirect map and every CTA depend on it. Needed at kickoff. The 1,000+ synopses figure. It appears only in the brief and is not corroborated on the current site. Confirm it, or tell us what to put in its place, before it goes on the homepage.

# 06  Payment schedule

| Milestone | Trigger | Share | Amount | Expected |
| --- | --- | --- | --- | --- |
| On signing | Contract executed, kickoff booked | 40% | ₹1,14,000 | Week 1 |
| On design approval | Gate 1 — written design sign-off | 30% | ₹85,500 | Week 3 |
| On launch | Gate 2 — site live | 30% | ₹85,500 | Week 7 |
| Phase 1 total |  | 100% | ₹2,85,000 |  |

All amounts exclude GST. Pricing is placeholder pending Vaelo’s confirmed rate card.

## Third-party costs, paid by Pharmatiya

| Item | Cost | Needed by |
| --- | --- | --- |
| Licensed typeface | ~$200–500 one-time | Week 2 |
| Hosting and domain | Depends on provider | Week 5 |
| Calendar booking tool | ~$10–15 / month | Week 4, if used |
| Email platform for the Digest | Free tier likely sufficient | Week 4 |

# 07  Risks and how each is handled

| Risk | Impact | Handling |
| --- | --- | --- |
| Case studies never arrive | Evidence page loses its strongest section — and Evidence is the page the primary buyer came for | Section ships omitted, not filled. Nothing is invented. We will offer a structured interview to draft cases from your recollection for your approval, which needs a 90-minute call in Week 4. |
| Dataset clearance withheld | Coverage claims become generic; a key credibility signal is lost | Dataset types always display. Named sources only where cleared. The page works either way, less persuasively without names. |
| No team photography | About cannot answer “is this a real firm?” visually for the referral visitor | Typographic treatment with names and credentials. No stock portraits under any circumstance. A local photographer is ~half a day if you want one. |
| Compliance review slower than the build | NextGen AI trust claims cannot be published; the page ships incomplete | Why input 9 is a Week-1 item: we need the turnaround time to schedule submission, not the review itself. Claims are drafted early and submitted in Week 4. |
| Gate feedback fragmented or late | Direct day-for-day slip on launch | One named reviewer consolidates internal feedback into a single response. One revision round is included at Gate 1. |
| Scope grows during build | Weeks 4–5 overrun; QA compresses; quality drops where it is least visible | The out-of-scope list in the brief holds. Additions are quoted as Phase 2 rather than absorbed. |
| Squarespace cancelled before DNS propagates | Site downtime during a live cutover | New site verified on a staging domain first; Squarespace stays active for 7 days after go-live. |

# 08  Definition of done

Launch is not “the pages exist”. Every item below is verified before go-live, and each maps to a defect found in the audit.

| Check | Standard | Fixes |
| --- | --- | --- |
| Lead capture | All three contact routes deliver a test enquiry to a confirmed inbox | Zero forms on the current site |
| Booking | Consultation CTA reaches a working booking or request path from every page | “Schedule your appointment” is not a link today |
| Digest | Subscription writes to a real list and sends a confirmation | Mentioned twice, captures nothing |
| Navigation | All six pages reachable from every page; Services in the primary nav | Services is currently orphaned |
| Deep links | Each homepage service teaser lands on its own service anchor | All three point at one page today |
| Images | No image has placeholder alt text; every alt describes the content | Five images read “Placeholder” |
| Headings | One H1 per page, strictly descending outline | Homepage has five H1s and no H2 |
| Contrast | 4.5:1 body, 3:1 large text and UI borders | WCAG AA requirement |
| Keyboard | Every interactive element reachable and visibly focused; mobile menu traps and restores focus | WCAG AA requirement |
| Responsive | No horizontal overflow at 320, 375, 768, 1024, 1280, 1440+ | Long medical terminology is the stress case |
| Logo | Vector, sharp at all densities, with a favicon set | Currently a raster JPEG |
| Cart | No cart, no /cart route, no e-commerce markup anywhere | Template remnant on every page |
| Redirects | Every old URL resolves 301 to its new equivalent | Preserves search equity |
| Performance | Core Web Vitals pass on mobile; no unnecessary JavaScript | Static-first requirement |
| Claims | No unverified figure, dataset name or outcome published | Fabrication guard |

# 09  After Phase 1

Out of scope here, noted so the sequence is visible. Nothing below is committed or quoted.

| Phase | Scope | Depends on |
| --- | --- | --- |
| Phase 2 | Brand identity — logo, palette, brand guidelines | Phase 1 live; identity gaps evidenced by real use |
| Phase 3 | NextGen AI product development, onboarding, audit trail; client portal or login | Product roadmap, not a website decision |
| Ongoing | Blog or CMS, content writing, SEO retainer, video | Whether Pharmatiya intends to publish regularly |
| Recommended | Utility pages: privacy, terms, accessibility statement | Small; can be added in Week 6 if you want them at launch |

The architecture is approved and the wireframes are signed off. What determines the 23 October launch date now is not design or build capacity — it is whether the three Week-1 inputs land by Friday 11 September, and whether the two gates close on schedule.

Vaelo Creative · hello@vaelocreative.com · Working document — pending rate card confirmation.